IMPERFECT ORG

OPERATIONS BIBLE

Puerto Rico's Premier Hero Shooter Team  ·  Est. 2017  ·  Overwatch 2  ·  Marvel Rivals

discord.gg/VuTAEqPT  ·  imperfect-sage.vercel.app/en

This document is the complete internal reference for IMPerfect Org. It covers the organization's 6-month launch roadmap, player agreements, code of conduct, and Discord server setup. Every player, coach, and staff member should read the chapters relevant to their role.

| Ch. | Contents | Topic |
| --- | --- | --- |
| 1 | Project Plan & 3-Phase Roadmap | Roadmap |
| 2 | Player Agreement | Team Ops |
| 3 | Code of Conduct | Team Ops |
| 4 | Discord Server Guide & Onboarding | Community |

CHAPTER 1

IMPERFECT ORG

Project Plan & 3-Phase Roadmap

6-month launch strategy  ·  Task tracker  ·  KPIs  ·  Risk register

This document outlines the full project plan and phased roadmap for launching and scaling IMPerfect Org over a 3–6 month period. The org is already partially launched and will focus on competitive team development, content creation, sponsorship acquisition, and community growth.

The plan is divided into three phases: Foundation & Brand (Months 1–2), Growth & Competition (Months 3–4), and Scale & Monetize (Months 5–6). Each phase contains specific, actionable tasks with assigned owners and timelines.

1.  PHASE 1 — FOUNDATION & BRAND

Months 1–2  |  Priority: Branding, Social Media, Sponsorship Outreach

Phase 1 focuses on solidifying organizational identity, establishing a credible digital presence, and beginning initial outreach to potential sponsors.

1.1 Branding & Identity

- Finalize org name, logo, and visual identity system (colors, typography, style guide)

- Design team jerseys, merch mockups, and branded assets for social/streaming

- Build or update org website with roster, about page, and contact/sponsorship info

- Create brand guidelines document for consistent use across all channels

1.2 Social Media & Content Foundation

- Claim handles on Twitter/X, Instagram, TikTok, YouTube, and Discord

- Set up Discord server with structured channels: announcements, general, team-specific, community

- Define content pillars: highlights, behind-the-scenes, player spotlights, event coverage

- Establish a weekly content calendar and assign a content lead

- Launch introductory posts and team reveal content

1.3 Sponsorship Outreach

- Build a sponsorship deck with audience demographics, org vision, and partnership tiers

- Identify 20–30 target sponsors: gaming peripherals, energy drinks, apparel, local brands

- Begin outreach via email and social DMs; track responses in a CRM spreadsheet

- Set up org email addresses and professional communication templates

Phase 1 Task Tracker:

| Task | Owner | Timeline | Status |
| --- | --- | --- | --- |
| Finalize logo & brand guide | Creative Lead | Week 1–2 | IN PROGRESS |
| Build/update org website | Web Lead | Week 2–4 | IN PROGRESS |
| Set up all social channels | Social Lead | Week 1 | DONE |
| Discord server setup | Community Manager | Week 1–2 | DONE |
| Create sponsorship deck | Business Lead | Week 2–3 | DONE |
| Begin sponsor outreach (20 targets) | Business Lead | Week 3–6 | TO DO |
| Launch content calendar | Content Lead | Week 2 | TO DO |
| Team reveal posts | Social Lead | Week 3–4 | TO DO |

2.  PHASE 2 — GROWTH & COMPETITION

Months 3–4  |  Priority: Team Development, Content Growth, First Sponsorships

Phase 2 shifts focus toward competitive performance and audience growth. Teams begin participating in tournaments, content production ramps up, and first sponsorship deals are finalized.

2.1 Competitive Teams

- Finalize rosters for all active game titles

- Set up practice schedules, scrim calendars, and VOD review sessions

- Register for upcoming open qualifiers and online leagues

- Hire or appoint a team manager or coach per division

2.2 Content Production

- Begin weekly YouTube/TikTok uploads: highlights, player profiles, tournament recaps

- Launch Twitch/YouTube live streams of scrims and ranked games

- Engage community in Discord with weekly events, watch parties, giveaways

- Reach 500 Discord members and 1,000 followers across social platforms

2.3 Sponsorship Closing

- Follow up on all Phase 1 outreach; aim to close 2–3 initial sponsors

- Negotiate contra deals (free product) as entry-level sponsorships

- Integrate sponsor branding into jerseys, stream overlays, and social posts

Phase 2 Task Tracker:

| Task | Owner | Timeline | Status |
| --- | --- | --- | --- |
| Finalize all team rosters | Team Manager | Month 3, Week 1 | TO DO |
| Register for 3+ tournaments | Team Manager | Month 3 | TO DO |
| Launch weekly content uploads | Content Lead | Month 3 onward | TO DO |
| Start streaming schedule | Content Lead | Month 3 | TO DO |
| Close first 2–3 sponsors | Business Lead | Month 3–4 | TO DO |
| Reach 1K social followers | Social Lead | End of Month 4 | TO DO |
| Discord 500 member milestone | Community Manager | Month 4 | TO DO |
| Appoint coaches per team | Org Director | Month 3 | TO DO |

3.  PHASE 3 — SCALE & MONETIZE

Months 5–6  |  Priority: Revenue, Brand Authority, Community Scale

Phase 3 is about building sustainable revenue, scaling the brand, and solidifying the org's reputation.

3.1 Revenue & Sponsorships

- Expand to 5–8 active sponsors with formal contracts

- Launch merchandise store (Printful or custom)

- Explore Twitch/YouTube monetization, affiliate deals, and tournament prize income

- Create tiered community membership with Discord perks

3.2 Competitive Growth

- Enter LAN events, regional championships, or higher-tier online leagues

- Build org reputation through consistent tournament placings

- Evaluate adding new game titles or expanding existing rosters

3.3 Brand & Community Authority

- Reach 5,000+ Discord members and 10,000+ combined social followers

- Partner with other orgs or creators for cross-promotional content

- Begin press outreach: esports media, game-specific publications

Phase 3 Task Tracker:

| Task | Owner | Timeline | Status |
| --- | --- | --- | --- |
| Scale to 5–8 sponsors | Business Lead | Month 5–6 | TO DO |
| Launch merch store | Business Lead | Month 5 | TO DO |
| Enter LAN / regional events | Team Manager | Month 5–6 | TO DO |
| 10K combined social followers | Social Lead | End of Month 6 | TO DO |
| 5K Discord members | Community Manager | End of Month 6 | TO DO |
| Media / press outreach | Business Lead | Month 6 | TO DO |
| Community membership program | Community Manager | Month 5 | TO DO |
| Org highlight reel | Content Lead | Month 6 | TO DO |

4.  KEY PERFORMANCE INDICATORS (KPIS)

| Metric | Month 2 Goal | Month 4 Goal | Month 6 Goal |
| --- | --- | --- | --- |
| Social Media Followers | 500 | 2,500 | 10,000+ |
| Discord Members | 100 | 500 | 5,000+ |
| Active Sponsors | 0 | 2–3 | 5–8 |
| Tournaments Entered | 0 | 3+ | 8–10+ |
| Monthly Content Pieces | 4 | 8 | 12+ |
| Monthly Revenue ($) | $0 | $500+ | $2,000+ |

5.  RISKS & MITIGATIONS

| Task | Owner | Timeline | Status |
| --- | --- | --- | --- |
| Player roster instability | Team Manager | Ongoing | MONITOR |
| Slow sponsorship responses | Business Lead | Month 2–3 | MONITOR |
| Content burnout / inconsistency | Content Lead | Ongoing | MONITOR |
| Budget overrun | Org Director | Monthly review | MONITOR |
| Low community engagement | Community Manager | Month 3 | MONITOR |

CHAPTER 2

IMPERFECT ORG

Player Agreement

Binding agreement between IMPerfect Org and all active roster members

|  | This agreement is a binding contract between IMPerfect Org and the player named below. Both parties should read it carefully before signing. This document is confidential and should not be shared outside the organization. |
| --- | --- |

1.  PLAYER INFORMATION

Complete all fields below before signing.

Full Legal Name

In-Game Name (IGN)

| Email Address |  | Discord Username |
| --- | --- | --- |

| Game Title(s) |  | Role / Position |
| --- | --- | --- |

| Agreement Start Date |  | Agreement End Date (or 'Ongoing') |
| --- | --- | --- |

2.  PLAYER COMMITMENTS

By signing this agreement, the Player agrees to fulfill the following responsibilities:

2.1 Availability & Practice

- Attend all scheduled team practice sessions unless excused in advance

- Communicate scheduling conflicts at least 48 hours in advance when possible

- Maintain a minimum attendance rate of 75% for scheduled practices and events

- Be available and ready at the agreed start time for all sessions

2.2 Competition

- Compete in all officially registered tournaments and league matches unless excused

- Give full competitive effort in every match — throwing or sandbagging is prohibited

- Follow all in-game rules and tournament regulations

- Notify the team manager immediately if unable to compete in a scheduled event

2.3 Conduct & Representation

- Represent IMPerfect Org professionally in all public-facing activities

- Use the organization's official tag and branding as directed when competing

- Refrain from making public statements that could damage the organization's reputation

- Follow the IMPerfect Org Code of Conduct (Chapter 3) at all times

2.4 Content & Media

- Participate in organization content when requested — spotlights, social posts, streams

- Tag or credit IMPerfect Org when posting content related to org activities

- Not represent another competitive team in the same game title without written consent

2.5 Communication

- Respond to official team communications within 24 hours on weekdays

- Maintain active presence in the team's official Discord server

- Report issues that may affect performance or availability to the team manager promptly

3.  ORGANIZATION COMMITMENTS

IMPerfect Org agrees to provide the following in return:

- Roster placement on the official IMPerfect Org team for the agreed game title(s)

- Access to organization branding assets, jerseys (if/when available), and team infrastructure

- Coaching, scrim coordination, and competitive support where available

- Entry fees covered for officially sanctioned tournaments where the org registers the team

- A transparent, respectful team environment governed by the Code of Conduct

- Clear communication of any roster decisions — no player dropped without prior conversation

- Credit and visibility in all org content featuring the player

4.  EXCLUSIVITY & OUTSIDE ACTIVITY

The Player agrees not to compete for or represent another esports organization in the same game title(s) during the term of this agreement without prior written approval from IMPerfect Org leadership.

The Player may stream, create content, and participate in ranked solo/duo play freely. Participation in pick-up teams or informal community tournaments is permitted provided it does not conflict with IMPerfect Org's schedule.

5.  BRANDING & INTELLECTUAL PROPERTY

The Player grants IMPerfect Org the right to use their IGN, likeness, and in-game clips for promotional and organizational content during the term of this agreement. IMPerfect Org will not use the Player's real name or personal social media accounts for commercial purposes without separate written consent.

6.  TERMINATION & ROSTER CHANGES

6.1 By the Player

The Player may leave the roster at any time by providing written notice to the team manager. A 7-day notice period is requested to allow the organization to plan for roster changes.

6.2 By the Organization

IMPerfect Org may release a player for: repeated Code of Conduct violations, sustained unavailability, public reputational damage, or mutual agreement. The org commits to a conversation with the player before any release decision is finalized.

6.3 Upon Termination

Upon departure, the Player must cease using IMPerfect Org branding, tags, and official titles immediately.

7.  AMENDMENTS & GOVERNING PRINCIPLES

This agreement may be updated by IMPerfect Org with 14 days' written notice. This agreement is entered into in good faith. In the event of a dispute, both parties agree to first attempt resolution through direct conversation.

|  | This agreement is not a formal legal contract and does not create an employment relationship. IMPerfect Org players are volunteer members of a competitive esports team. This document outlines mutual expectations and commitments in good faith. |
| --- | --- |

8.  SIGNATURES

By signing below, both parties confirm they have read, understood, and agreed to the terms of this Player Agreement.

Player

| Player Full Name & IGN | Date |
| --- | --- |

IMPerfect Org Representative

| Name & Role | Date |
| --- | --- |

CHAPTER 3

IMPERFECT ORG

Code of Conduct

Applies to all players, staff, and community members

IMPerfect Org was built in Puerto Rico with the belief that competitive excellence and community respect go together. This Code of Conduct defines the standards of behavior expected from every member of the organization.

|  | These rules exist to protect our players, our community, our sponsors, and the reputation of the org. Ignorance of these rules is not an excuse. If you are unsure whether something is acceptable, ask before acting. |
| --- | --- |

1.  RESPECT & INCLUSION

Required

- Treat all teammates, opponents, staff, and community members with respect at all times

- Use inclusive, welcoming language in all official org spaces

- Support and uplift your teammates — this is a team environment, not an individual showcase

Prohibited

- Harassment, bullying, or targeted personal attacks — in any form, on any platform

- Discrimination based on race, gender, nationality, religion, age, or sexual orientation

- Use of slurs, hate speech, or derogatory language in voice chat, text, or in-game

- Doxxing, sharing personal information, or threatening any person

2.  IN-GAME BEHAVIOR

Required

- Play every game with full effort and a competitive mindset

- Communicate clearly and constructively during matches

- Follow the shotcaller or in-game leader's calls during competitive play

- Accept losses graciously and wins humbly

Prohibited

- Intentional feeding, throwing, or griefing in any match

- Smurfing or account boosting in violation of game publisher terms of service

- Use of unauthorized software, scripts, macros, or exploits

- Verbal abuse, toxic chat, or unsportsmanlike behavior toward opponents or teammates

3.  SOCIAL MEDIA & PUBLIC CONDUCT

Required

- Use good judgment before posting anything that could be linked to the org

- Use official branding and tags as directed when posting org-related content

- Be respectful of other orgs, players, and the broader gaming community publicly

Prohibited

- Posts that attack, demean, or harass other players or organizations

- Sharing confidential org information — roster changes, sponsor discussions, internal conflicts

- Making statements on behalf of IMPerfect Org without authorization from leadership

- Posting hateful, discriminatory, or illegal content on any platform

4.  INTEGRITY & FAIR PLAY

- No match fixing, result manipulation, or collusion with opponents under any circumstances

- No unauthorized sharing of team strategies, draft information, or scrim results with opponents

- Report any approach by outside parties attempting to compromise competitive integrity immediately

5.  VIOLATIONS & CONSEQUENCES

| Level | Examples | Possible Consequence |
| --- | --- | --- |
| Minor | Late to practice, minor chat violation | Verbal reminder or written warning |
| Moderate | Repeated tardiness, public disrespect | Formal warning, probation, benching |
| Serious | Harassment, toxic behavior, repeated violations | Suspension, removal from active roster |
| Severe | Match fixing, hate speech, doxxing, threats | Immediate release from org |

6.  ACKNOWLEDGMENT

By joining or continuing as a member of IMPerfect Org, you agree to uphold this Code of Conduct.

| Player Full Name, IGN & Date | Date |
| --- | --- |

CHAPTER 4

IMPERFECT ORG

Discord Server Guide & Onboarding

Channel structure  ·  Role hierarchy  ·  Server rules  ·  Ready-to-paste messages

This chapter is the complete reference for setting up, managing, and onboarding members to the Imperfect Gaming Discord server. It covers channel structure, role hierarchy, server rules, moderation guidelines, and ready-to-paste messages.

1.  CHANNEL STRUCTURE

The server is organized into 7 categories. Copy this structure when setting up or auditing the server.

| Channel | Purpose |
| --- | --- |
| 📋 WELCOME & INFO |  |
| 👋 #welcome | First channel new members see. Auto-displays welcome message + server overview. |
| 📜 #rules | Server rules. Read-only. All members must read before getting full access. |
| 📣 #announcements | Official org announcements only. Admin/mod post only. |
| 🗺️ #roles | Role selection channel. Members pick game roles, pronouns, language pref. |
| 📰 #news | Esports news, patch notes, game updates. |
| 🏆 TEAM HQ |  |
| 🎮 #roster | Official roster list for all divisions. Pinned, kept up to date by staff. |
| 📅 #schedule | Practice times, tournament dates, scrims. Updated weekly by team manager. |
| 🏅 #results | Match results, tournament placements. Posted after every competitive event. |
| 📊 #tryouts | Tryout announcements, requirements, and application links. |
| 💬 GENERAL |  |
| 👾 #general | Main community chat. Most active channel. |
| 🎙️ #introductions | New members introduce themselves. Pinned intro format provided. |
| 😂 #memes | Gaming memes, funny clips, good vibes only. |
| 🔗 #clips-and-highlights | Post your best plays, VODs, and highlight clips. |
| 🎯 GAME CHANNELS |  |
| ⚔️ #overwatch-2 | OW2 discussion, hero meta, team comps, scrim talk. |
| 🦸 #marvel-rivals | MR strategy, roster updates, ranked grind talk. |
| 📈 #ranked-talk | Solo queue discussion, rank tracking, tips across all games. |
| 🧠 #strategy-room | VOD review links, team strats, draft notes. Team members only. |
| 🎉 COMMUNITY EVENTS |  |
| 🏟️ #community-tournaments | Community-run events, inhouses, watch parties. |
| 🎟️ #giveaways | Org and sponsor giveaways. Moderated. |
| 📺 #watch-party | Stream watch parties, game launch events, match viewing. |
| 🛠️ SUPPORT |  |
| ❓ #faq | Pinned answers to common questions. Read-only. |
| 📬 #contact-staff | Members can tag mods or submit questions. |
| 🚨 #report | Report rule violations, toxic behavior. Monitored by mods. |
| 🔒 STAFF ONLY (HIDDEN) |  |
| 📋 #staff-general | Staff & mod general chat. Internal coordination. |
| 📌 #mod-log | Log of moderation actions — warns, kicks, bans. |
| 📨 #sponsor-leads | Sponsor outreach tracking and contact notes. |
| 🗓️ #team-manager | Coach/manager communication, practice notes, lineup decisions. |

|  | Set #welcome, #rules, and #announcements as read-only for @everyone. New members should only be able to type in #introductions and #general until they accept the rules and get verified. |
| --- | --- |

2.  ROLE HIERARCHY

Roles control permissions, channel access, and display order in the member list. Assign from top to bottom.

|  | Role | Who Gets It | Key Permissions |
| --- | --- | --- | --- |
|  | Founder | Org leadership only | All permissions — full admin |
|  | Admin | Org directors & managers | Manage channels, roles, bans |
|  | Moderator | Trusted staff, selected mods | Kick, mute, manage messages |
|  | Head Coach | Head coach per division | Access all team channels + staff |
|  | Coach / Analyst | Coaches, VOD reviewers | Access team & strategy channels |
|  | OW2 Roster | Active Overwatch 2 players | OW2 team channels + voice |
|  | MR Roster | Active Marvel Rivals players | MR team channels + voice |
|  | Sub / Trial | Trial players on probation | Team channels read-only |
|  | Content Creator | Org streamers & content staff | Post in media channels |
|  | Community Member | Verified members (default) | Read + chat in public channels |
|  | Unverified | New members, pending rules | #welcome and #rules only |

3.  WELCOME MESSAGE

Post in #welcome. Pin it at the top of the channel.

WELCOME TO IMPERFECT GAMING 🇵🇷 Puerto Rico's #1 competitive hero shooter org — est. 2017. We compete in Overwatch 2 and Marvel Rivals at the highest regional level. GET STARTED 1. Read the rules in #rules and react with ✅ to unlock the server 2. Pick your roles in #roles (game, language, pronouns) 3. Introduce yourself in #introductions 4. Jump into #general and say hi! 🌐 Website → imperfect-sage.vercel.app/en 🎮 Tryouts → #tryouts ¦ ❓ Help → #faq or #contact-staff Representing the island. Competing with the world. 💚

4.  SERVER RULES

Post in #rules as a pinned message. Members must react with ✅ to gain the Community Member role.

IMPERFECT GAMING — SERVER RULES 1. RESPECT EVERYONE — No harassment, bullying, hate speech, or targeted attacks. 2. ENGLISH & SPANISH WELCOME — We are a PR org. Don't police anyone's language. 3. NO SPAM OR SELF-PROMOTION — No promoting streams/servers without staff permission. 4. KEEP CHANNELS ON TOPIC — Off-topic posts will be deleted. 5. NO NSFW CONTENT — No explicit or adult content anywhere. 6. NO CHEATING DISCUSSION — Promoting hacks or exploits = instant ban. 7. LISTEN TO STAFF — Disputes go to #contact-staff, not public channels. 8. NO DRAMA — Keep personal conflicts out of public channels. 9. PROTECT PRIVACY — No doxxing or sharing private conversations. 10. HAVE FUN — Built by gamers, for gamers. Rep the island. 🇵🇷 React with ✅ below to confirm you've read the rules and unlock the server.

5.  INTRODUCTION TEMPLATE

Pin this in #introductions so new members know what to post.

NEW HERE? DROP YOUR INTRO BELOW 👋 IGN / Handle: Games I play: Main role / hero: Current rank: From: Something about me: Here to: [ ] Just vibe [ ] Community grind [ ] Try out [ ] Create content Welcome to Imperfect Gaming. Built in Puerto Rico, competing with the world. 🇵🇷

6.  MODERATION GUIDELINES

Escalation Ladder

- Verbal reminder in channel (minor, first offense)

- Official warning via DM — log in #mod-log with date and reason

- Temp mute (1–24 hours) — for repeat offenders or heated situations

- Kick — for serious violations or failure to respond to warnings

- Ban — for severe violations (hate speech, doxxing, threats)

Mod Log Format

MOD ACTION LOG Date: [DD/MM/YYYY] Mod: [Your name / Discord tag] User: [Username + Discord ID] Action: [Warn / Mute / Kick / Ban] Reason: [Brief description] Evidence: [Screenshot link or description]

Golden Rules for Mods

- Never moderate situations involving yourself — hand to another mod

- Don't argue with members publicly — take it to DMs

- Be consistent — apply the same standard to everyone, no favorites

- Document everything — a well-kept #mod-log protects the whole team

Imperfect Gaming  ·  Operations Bible  ·  Est. 2017  ·  Puerto Rico  ·  Internal Use Only